## Phase1 Planner
Day | Week | Date Offset | Module | Task | Priority | Est Hours | Status | Notes
1 | 1 | Day 1 | Setup | Finalize stack, create repo, folders | High | 3 | Not Started
2 | 1 | Day 2 | Frontend | React + Tailwind setup | High | 3 | Not Started
3 | 1 | Day 3 | Backend | API setup & structure | High | 3 | Not Started
4 | 1 | Day 4 | Database | Supabase/Postgres schema init | High | 3 | Not Started
5 | 1 | Day 5 | Auth | Login + roles | High | 3 | Not Started
6 | 1 | Day 6 | UI | Dashboard shell | High | 5 | Not Started
7 | 1 | Day 7 | Review | Test & cleanup | High | 5 | Not Started
8 | 2 | Day 8 | Tasks | Create task form | High | 3 | Not Started
9 | 2 | Day 9 | Tasks | Task list page | High | 3 | Not Started
10 | 2 | Day 10 | Tasks | Status update flow | High | 3 | Not Started
11 | 2 | Day 11 | Scheduler | Assign engineer to tasks | High | 3 | Not Started
12 | 2 | Day 12 | Scheduler | Team workload page | High | 3 | Not Started
13 | 2 | Day 13 | Scheduler | Leave/availability tracker | High | 5 | Not Started
14 | 2 | Day 14 | Review | Bug fixing | High | 5 | Not Started
15 | 3 | Day 15 | Meetings | Meeting create page | High | 3 | Not Started
16 | 3 | Day 16 | Meetings | Agenda + notes | High | 3 | Not Started
17 | 3 | Day 17 | Meetings | Reminders | High | 3 | Not Started
18 | 3 | Day 18 | Dashboard | KPI cards | High | 3 | Not Started
19 | 3 | Day 19 | Dashboard | Charts integration | High | 3 | Not Started
20 | 3 | Day 20 | Reports | Daily report export | High | 5 | Not Started
21 | 3 | Day 21 | Reports | Weekly report page | High | 5 | Not Started
22 | 4 | Day 22 | Alerts | Overdue task alerts | High | 3 | Not Started
23 | 4 | Day 23 | Alerts | Missing status alerts | High | 3 | Not Started
24 | 4 | Day 24 | Alerts | Telegram/email notifications | High | 3 | Not Started
25 | 4 | Day 25 | UI | Responsive polish | High | 3 | Not Started
26 | 4 | Day 26 | QA | Full bug fixing | High | 3 | Not Started
27 | 4 | Day 27 | QA | Real sample data testing | High | 5 | Not Started
28 | 4 | Day 28 | Deploy | Deploy frontend/backend | High | 5 | Not Started
29 | 4 | Day 29 | Pilot | Use personally one day | High | 3 | Not Started
30 | 4 | Day 30 | Launch | Final fixes + complete | High | 3 | Not Started

## Summary
Metric | Value
Total Days | 30
Weeks | 4
Recommended Weekday Hours | 3
Recommended Weekend Hours | 5
Total Planned Hours | ~100+
Goal | Complete Phase 1 MVP